## Unique Issues
ID | Issue Name | Where Is the Issue | Representative Lines | Why This Is an Issue | Category | Severity | Status | Estimated Effort | How to Solve | Example Fix / Guidance | Verification | Owner | Resolution Status | SonarQube Link
1 | Use "Annotated" type hints for FastAPI dependency injection | app/admin/architecture_rules/router.py; app/admin/disadmin/router.py; app/admin/disclaimer/router.py; app/admin/eligibility/router.py; app/admin/superadmin/router.py; app/domains/account_details/router.py; app/domains/architecture/router.py; app/domains/auth/router.py; app/domains/cloud_resources/router.py; app/domains/onboarding/router.py; app/domains/requirements/router.py | Multiple lines, including L16-L226 | Using dependency objects directly as default values mixes type information with runtime dependency metadata. Annotated keeps the real type explicit, improves editor support, and follows current FastAPI conventions. | Maintainability | Blocker | Open | 15 min per occurrence | Import Annotated and move Depends(...) or another FastAPI dependency marker into the annotation. Keep the parameter default-free unless a real default is required. | Before: db: Session = Depends(get_db) After: db: Annotated[Session, Depends(get_db)] | Run unit/API tests, regenerate OpenAPI, and rerun SonarQube. |  | Not Started | https://ismartams.tcsapps.com/sonarqube/project/issues?id=CLOUD_ONBOARDING-backend
2 | Remove redundant response_model parameter when it duplicates the return annotation | app/admin/architecture_rules/router.py; app/admin/disadmin/router.py; app/admin/disclaimer/router.py; app/admin/eligibility/router.py; app/admin/superadmin/router.py; app/domains/account_details/router.py; app/domains/architecture/router.py; app/domains/auth/router.py; app/domains/cloud_resources/router.py; app/domains/onboarding/router.py; app/domains/requirements/router.py | Multiple decorator lines, including L15-L179 | Declaring the same response schema in both response_model and the function return annotation duplicates information and can drift during maintenance. | Maintainability | Blocker | Open | 10 min per occurrence | Keep the typed return annotation and remove response_model from the route decorator, provided both express exactly the same schema and behavior. | Before: @router.get("/x", response_model=Item) def get_x() -> Item: ... After: @router.get("/x") def get_x() -> Item: ... | Check generated OpenAPI schema and response filtering, then rerun tests and SonarQube. |  | Not Started | https://ismartams.tcsapps.com/sonarqube/project/issues?id=CLOUD_ONBOARDING-backend
3 | Remove and rotate hard-coded PostgreSQL password | app/core/config.py | L9, L10 | A database password committed in source control can be exposed through repository access, logs, build artifacts, or history. Removing it from only the latest file does not invalidate an exposed credential. | Security | Blocker | Open | 30 min per occurrence | Immediately rotate the database credential. Read the replacement from a secret manager or environment variable. Remove the secret from code and, where required, purge it from repository history. | Use a settings field such as POSTGRES_PASSWORD loaded from the deployment secret store. Never commit the actual value or a real .env file. | Confirm the old credential no longer works, scan repository history, run secret scanning, and rerun SonarQube. |  | Not Started | https://ismartams.tcsapps.com/sonarqube/project/issues?open=628e94b7-a93e-4983-8140-f2009d9b2f85&id=CLOUD_ONBOARDING-backend
4 | Define a constant instead of duplicating the literal 'now()' 6 times | alembic/versions/783e123ab7dd_initial_models.py | L40 | Repeated literals create multiple maintenance points and increase the risk of inconsistent edits. | Maintainability | High | Open | 12 min | Define a module-level constant for the SQL expression and reuse it in the migration definitions. | NOW_SQL = "now()" Use NOW_SQL wherever the same literal is required. | Run migration upgrade/downgrade tests and compare generated database defaults. |  | Not Started | https://ismartams.tcsapps.com/sonarqube/project/issues?open=8dbaa920-464c-41c0-a57e-2bb61afa06c7&id=CLOUD_ONBOARDING-backend
5 | Define constants for duplicated not-found message literals | app/admin/architecture_rules/router.py; app/admin/disadmin/router.py; app/admin/disclaimer/router.py; app/admin/eligibility/router.py; app/domains/onboarding/router.py | L43, L47, L53, L104 and related occurrences | Repeated error text such as "Rule not found", "Onboarding not found", "Clause not found", and "Question not found" is harder to update consistently and can produce inconsistent API messages. | Maintainability | High | Open | 6-10 min per literal group | Create clearly named constants, preferably in the owning module or a shared error-message module when genuinely reused across modules. | RULE_NOT_FOUND = "Rule not found" ONBOARDING_NOT_FOUND = "Onboarding not found" | Run endpoint tests and confirm response detail text is unchanged. |  | Not Started | https://ismartams.tcsapps.com/sonarqube/project/issues?id=CLOUD_ONBOARDING-backend
6 | Document HTTPException status codes in FastAPI responses | Multiple FastAPI router modules listed in the scan | Status codes 400, 403, 404, 409 and 500 across multiple lines | Undocumented error responses make the generated OpenAPI contract incomplete. API consumers cannot reliably discover possible failure codes and schemas. | Maintainability | High | Open | 10-15 min per occurrence | Add the raised status code to the route decorator responses mapping. Reuse a standard error model and shared response dictionaries where appropriate. | @router.get("/x", responses={404: {"description": "Not found"}}) def get_x(...) -> Item: ... | Inspect /openapi.json or Swagger UI, test each error path, and rerun SonarQube. |  | Not Started | https://ismartams.tcsapps.com/sonarqube/project/issues?id=CLOUD_ONBOARDING-backend
7 | Reduce function Cognitive Complexity from 48 to 15 | app/admin/disadmin/service.py | L492 | Deep nesting, many branches, and mixed responsibilities make the function difficult to understand, test, and safely change. | Maintainability | High | Open | 38 min | Extract cohesive helper functions, use guard clauses, flatten nested conditionals, separate validation from transformation/persistence, and replace long conditional chains with mappings or strategy functions where suitable. | Split the function into orchestration plus small helpers such as validate_input(), build_entities(), persist_changes(), and format_result(). | Add focused tests for each branch, run coverage, and confirm Sonar complexity is 15 or lower. |  | Not Started | https://ismartams.tcsapps.com/sonarqube/project/issues?open=e90ec360-1fe6-49e5-b10b-73660247c813&id=CLOUD_ONBOARDING-backend
8 | Reduce function Cognitive Complexity from 16 to 15 | app/core/llm.py | L127 | The function is slightly above the allowed complexity threshold and is harder to follow than necessary. | Maintainability | High | Open | 6 min | Use an early return or extract one conditional block into a well-named helper, while preserving behavior. | Move one independent branch into a helper and keep the main function as a short orchestration flow. | Run LLM-related unit tests and confirm Sonar complexity is 15 or lower. |  | Not Started | https://ismartams.tcsapps.com/sonarqube/project/issues?open=4e0fccda-25d4-4ea1-a240-d2bbaaeba997&id=CLOUD_ONBOARDING-backend
9 | Define a constant for duplicated SQLAlchemy cascade literal "all, delete-orphan" | app/models/onboarding.py | L56 | Repeating the relationship cascade string nine times creates unnecessary duplication and makes a future policy change error-prone. | Maintainability | High | Open | 18 min | Define a descriptive module-level constant and reuse it in each relationship declaration. | DELETE_ORPHAN_CASCADE = "all, delete-orphan" | Run ORM relationship and deletion tests, including orphan removal behavior. |  | Not Started | https://ismartams.tcsapps.com/sonarqube/project/issues?open=37d53cf1-385c-4497-b6bf-99646b413aff&id=CLOUD_ONBOARDING-backend

## Summary
SonarQube Remediation Summary
Metric | Value | Notes | Priority
Unique issue patterns | 9 | Consolidated from the supplied SonarQube export
Blocker patterns | 3 | Resolve first | P0
High patterns | 6 | Resolve after blockers | P1
Security patterns | 1 | Rotate exposed credentials immediately | P0
Resolved patterns | 0 | Update Resolution Status in Unique Issues
Open patterns | 11 | Current unique patterns not marked resolved

## Notes & Assumptions
Topic | Details
Purpose | A remediation tracker containing one row per unique SonarQube issue pattern found in the supplied export.
Consolidation | Repeated occurrences of the same rule are grouped. Exact file and line occurrences remain available in SonarQube through the supplied links.
Coverage | The supplied text shows 154 Blocker occurrences and 52 High occurrences. This workbook intentionally catalogs unique remediation patterns rather than reproducing every occurrence.
Important security action | For the PostgreSQL password finding, rotate the credential before or at the same time as removing it from source. Removing the string alone is insufficient.
Suggested workflow | Filter by Severity, assign an Owner, update Resolution Status, implement the fix, verify tests/OpenAPI/migrations as applicable, then rerun SonarQube.